## Roadmap
# | Month | Phase | FDE Topic | Project Deliverable | Stack | Status | Done Date | Notes / Learnings
1 | 1 | Discover | FDE role, customer discovery, requirements elicitation | Requirements doc, stakeholder map, success metrics | Docs | Done | 2026-10-14 | Requirements + decisions finalized (01-requirements.md)
2 | 1 | Discover | Legacy data profiling, data quality, schema analysis | Sample legacy dataset + profiling report | Python, Oracle | Done | 2026-10-14 | Profile + cleansing plan: docs/02-*.md
3 | 1 | Design | System design, ADRs, risk register | Architecture doc, ADRs, risk register | Docs | Done | 2026-10-14 | docs/03-architecture.md with 6 ADRs, state machine
4 | 2 | Design | Data modeling, Liquibase, multi-tenancy | Oracle schema + changelogs, tenant model | Oracle, Liquibase | Done | 2026-10-14 | Liquibase changelogs (9 tables)
5 | 2 | Design | API design, OpenAPI, event contracts | OpenAPI specs, Kafka topic/event schemas | Spring Boot, Kafka | Done | 2026-10-14 | docs/contracts: OpenAPI + Kafka events
6 | 2 | Build | Project skeleton, CI, Docker, config mgmt | Mono-repo, docker-compose, CI pipeline | Docker | Done | 2026-10-14 | 3 services scaffolded + tested/built, CI file added. Docker compose for Kafka/Debezium still pending (Docker not installed)
7 | 3 | Build | Bulk load, batching, performance tuning | Initial-load engine | Spring Boot, Oracle | Done | 2026-10-14 | 66k rows on H2: per-row 5.3s vs JDBC batch 5.0s (in-memory DB has no network cost, so little gain). Batch mode is default (migration.load.batch-insert), per-row kept as fallback; both tested. Real gain must be measured on Oracle
8 | 3 | Build | CDC, Kafka, ordering, idempotency | CDC sync pipeline with replay | Kafka | Blocked |  | Needs Docker (Kafka/Debezium/Postgres)
9 | 3 | Build | Schema mapping, transformations, validation | Mapping engine + AI mapping suggester | FastAPI, Spring Boot | Done | 2026-10-14 | Wired end to end: orchestrator calls ai-service, humans approve in MIG_MAPPING, loader reads approved mappings for BORROWER (renamed-column fixture tests, 19 Java tests). Other entities use fixed columns; no real LLM tried
10 | 4 | Build | Shadow read, diffing, reconciliation | Reconciliation + diff engine, reports | Spring Boot, Oracle | Done |  | Reconciliation (counts+sums) plus field-level shadow read (GET /shadow-diff); READY blocked on any mismatch. Tested incl. injected drift. Not timed on 66k rows or Oracle
11 | 4 | Build | Cutover, rollback, feature flags, runbooks | Cutover/rollback orchestrator + runbook | Spring Boot | Done | 2026-10-14 | Done on H2: state machine with 3 pre-checks (mappings, shadow, reconciliation), approval gate, rollback only from FREEZE/FINAL_SYNC/SWITCHED/MONITOR, audit trail, runbook docs/04. Corners: ROLLED_BACK is terminal; guarded UPDATE stops racing transitions (no concurrency test, gap G7). Missing: feature flags, real traffic switch.
12 | 4 | Build | Resilience: retries, DLQ, backpressure | Failure handling + chaos tests | Kafka | In Progress |  | Done: AI client retries 5xx/network errors with exponential backoff (3 attempts, 200ms), never retries 4xx, then 502; LLM failure falls back to rules; per-batch transactions make the load restartable. Blocked (needs Kafka/Docker): DLQ, backpressure, consumer retries. Chaos coverage is limited to AI-down and LLM-down.
13 | 5 | Build | Observability: logs, metrics, traces, alerts | Datadog/Prometheus dashboards, alerts | Datadog | In Progress |  | Done: Micrometer counters migration.rows (entity,outcome), migration.rows.quarantined (entity,reason), migration.precheck.failed (check), migration.transitions (to), timer migration.load.duration; read at /actuator/metrics. Counted after commit so rolled-back batches are never counted. Not built: Prometheus/Datadog export, dashboards, traces, alert rules, structured logs.
14 | 5 | Build | LLM tool-calling, RAG, guardrails, evals | AI diagnosis agent (read-only tools, approval gate) | FastAPI, LLM | Done | 2026-10-14 | Rules-first agent: 6 allow-listed GET tools (get_run/reconciliation/exceptions/audit/mappings/shadow_diff). 13 causes incl. UNKNOWN (abstains). Symptom text outranks evidence patterns; dominant-exception threshold 50%. Shadow diff read only if something loaded. Partial tool failures recorded in evidence.errors, missing run -> 404, orchestrator down -> 502. Actions always requires_approval=True. LLM only narrates a PII-free summary; failure falls back to rules (llm_used=false). Symptom capped at 500 chars. 16/16 eval, 20 pytest, live-checked. Real LLM not tried.
15 | 5 | Build | React/TypeScript UI, UX for operators | Migration console: progress, diffs, agent chat | React, TS | Done | 2026-10-14 | Console complete: runs, stepper, badges, reconciliation, exceptions, mapping review, Diagnose panel, 5s polling, errors with role=alert. 19 unit tests + 2 Playwright e2e (real browser), screenshot in docs/screenshots. Gaps: no login (security S1), e2e needs ports 8081/8000/5173 free, desktop layout only.
16 | 6 | Test | Test strategy, contract, load, chaos, DR drill | Test reports, rollback drill, load results | JUnit, k6, pytest | Done | 2026-10-14 | docs/05: 39 Java, 27 Python, 23 console, 3 e2e (94 total) (Edge) + 16-scenario agent eval, all green on H2. Authentication added: Basic auth, roles OPERATOR/REVIEWER/APPROVER/READER, actor from login, SWITCHED needs APPROVER, no default DB password, agent uses READER service account (docs/06 S1, S2 closed in code). Lesson: a 401 with WWW-Authenticate makes browsers hang on fetch, so the API sends a bare 401 and the console verifies credentials at sign-in. Gaps: no Oracle run, no contract tests, no k6 load test, no CDC, no real LLM (Zscaler), no concurrency test. Added: ConcurrentTransitionTest (6 racing callers, 1 winner, 5 x 409) and ApiContractTest (code vs OpenAPI endpoints; found 6 undocumented endpoints). G2 partly and G7 closed.
17 | 6 | Test | Security: authn/z, secrets, audit, PII | Security review + fixes | Spring Security | In Progress |  | docs/06-security-review.md: controls proven by tests (read-only agent, PII-free LLM prompts, no raw rows in API, parameterised SQL, approval gates, audit). Findings S1-S9: S1 no authn/z (approver is typed text) and S2 default DB password block real data. Fixes not yet applied. Update: checklist now 13 items; CI green on GitHub (G6 closed); demo script docs/08; repo public at github.com/jeswinstaynes01-dev/migration-orchestrator. FR1 data profiling now built: GET /api/runs/{id}/profile (null rates, duplicates, date-format mix, counts only so PII-free) plus console Data profile panel; tests ProfileServiceTest and ProfilePanel.test.
18 | 6 | Signoff | Deployment, handover, customer comms | Deploy guide, ops handbook, demo, signoff | Docs | In Progress |  | docs/07-deployment-handover-signoff.md: deploy guide, config table, ops handbook with metrics and symptom table, 15-min demo script, COO status update, signoff checklist. Verdict: demo-ready, NOT production-ready. Open: Oracle rehearsal, CDC, authn, named customer approver, CI on GitHub.

## Learning Trace
# | Area | Technology / Topic | Where in this project | Hands-on trace exercise | Interview questions you must answer | Project status | Confidence (1-5) | My notes / STAR story
1 | FDE core | Requirements discovery | docs/01-requirements.md | Rewrite the 5 goals as a customer email; list 3 questions you'd ask on a discovery call. | How do you turn a vague customer complaint into measurable requirements? What do you do when requirements conflict? | Done
2 | FDE core | Data profiling & quality | legacy-data/profile_legacy_data.py, docs/02-data-profile.md | Add a new anomaly to the generator (e.g. duplicate payments), then make the profiler detect it. | A customer gives you messy data. What are your first 5 steps? How do you decide fix vs quarantine vs ask? | Done |  | Update: profiling is now an API (/api/runs/{id}/profile) and a console panel; reports counts only (no raw values) so it is PII-free; tested by ProfileServiceTest.
3 | FDE core | Cleansing & mapping decisions | docs/02-cleansing-plan.md | Pick 3 rows from the plan and justify each decision to a skeptical finance lead. | Why not silently fix money data? How do you get customer sign-off on data decisions? | Done
4 | FDE core | ADRs & trade-offs | docs/03-architecture.md (6 ADRs) | Write ADR-7 on your own: why batch size 1000 and per-batch transactions? | Tell me about a design decision you made and the trade-off. Why CDC over dual-write? | Done
5 | Data / DB | Oracle data modeling & constraints | orchestrator-service/.../001-business-tables.yaml | Add a CHECK that AMOUNT >= 0 on PAYMENT via a new changelog. Observe what breaks. | PK/FK/check constraints? Why NUMBER(14,2) for money? Why a tenant column on every table? | Done
6 | Data / DB | Liquibase migrations | db/changelog/*.yaml, SchemaMigrationTest | Write a changeSet that adds a column, run the test, then try to edit an already-run changeSet and read the checksum error. | Why never edit an applied changeSet? How do you roll back a schema change safely? | Done
7 | Data / DB | Idempotency & restartability | load/BulkLoader.java (MIG_ID_XREF), BulkLoaderTest | Kill the loader mid-run (throw in a batch) and re-run; prove no duplicates. | How do you make a data load safe to retry? Explain at-least-once vs exactly-once. | Done
8 | Data / DB | Bulk performance tuning | load/BulkLoader.java (per-row insert) | Load the 66k-row dataset, time it, switch to JDBC batchUpdate, compare. | A load is too slow. How do you find and fix the bottleneck? Batch size trade-offs? | Done on H2: batchUpdate + generated keys implemented, 5.3s -> 5.0s only (no network latency). Lesson: measure on the real DB. Oracle timing pending
9 | Backend | Spring Boot, DI, config | OrchestratorApplication.java, application.yml | Add a profile 'oracle' vs 'test' and switch DB with an env variable. | How does Spring wire beans? Where should secrets and config live? | Done
10 | Backend | Transactions (programmatic vs @Transactional) | BulkLoader.processBatch (TransactionTemplate) | Replace TransactionTemplate with @Transactional on a method in the same class; see why self-invocation fails. | Why does @Transactional not work on self-calls? What is the cost of one big transaction? | Done
11 | Backend | Parsing & validation (pure functions) | load/LegacyValueParser.java + test | Add a new date format and a test that fails first (TDD). | How do you design testable transformation code? What are two-digit-year pitfalls? | Done
12 | Backend | REST API & OpenAPI design | docs/contracts/orchestrator-openapi.yaml | Implement POST /api/runs and GET /api/runs/{id} against the contract. | Contract-first vs code-first? What status codes for pre-check failure vs approval required? | Done (9 endpoints, MockMvc tests)
13 | Backend | State machine for cutover | docs/03-architecture.md section 3 | Implement the transition table with pre-checks and an approval gate; test illegal transitions. | How do you model a risky multi-step process? Where is rollback possible and why? | Done (RunState + approval gate + tests)
14 | Streaming | Kafka fundamentals (keys, partitions, offsets) | docs/contracts/kafka-events.md | Produce 100 loan events with key=loan_id, consume with 2 consumers, confirm per-key ordering. | Why key by business id? What does consumer-group rebalance do? How do you replay? | Not yet built (needs Docker)
15 | Streaming | CDC with Debezium | docs/03-architecture.md ADR-1 | Update a row in Postgres; watch the event; find the LSN in the payload. | CDC vs dual-write vs polling? What happens if the connector is down for an hour? | Not yet built (needs Docker)
16 | Streaming | Retries, DLQ, backpressure | docs/contracts/kafka-events.md (DLQ envelope) | Inject a poison message; confirm 5 retries then DLQ, then replay it after the fix. | How do you handle poison messages? How do you prevent a retry storm? | Partially: AI-client retry with exponential backoff, 4xx not retried, then 502 (HttpAiClientRetryTest); restartable per-batch transactions. DLQ and backpressure need Kafka (blocked). Interview angle: retry only idempotent/transient failures; cap attempts; always surface the final error. Also proven: concurrent transition race gives exactly one winner (optimistic UPDATE ... WHERE STATE=?), others get 409.
17 | Reconciliation | Reconciliation & shadow reads | BulkLoaderTest invariant read = loaded + quarantined | Build a SUM(amount) comparison between legacy CSV and Oracle; deliberately corrupt one row and detect it. | How do you prove a migration is correct? What do you do about differences? | Done: counts, sums and field-level shadow diff gating READY
18 | AI | LLM tool-calling & RAG | ai-service/app/agent/{tools,diagnose,evals}.py, app/main.py (POST /agent/diagnose), console/src/DiagnosePanel.tsx | Build one read-only tool (get_exception_summary) and let an LLM call it. | How do you stop an agent doing something unsafe? RAG vs fine-tuning? What goes in an eval set? | Done (rules-first). Corners: allow-list of 6 GET-only tools, no write tool exists; 404/502 mapping; partial failures kept as evidence.errors; proposals always need approval; UI shows read-only banner; Ollama 0.40.4 installed locally but model pull blocked by corporate Zscaler (403 on registry.ollama.ai), so no real LLM tried yet. Client has a unit test for the Bearer header/model/temperature=0. Trace: UI button -> /ai proxy -> FastAPI -> GET calls to orchestrator -> rules -> JSON -> panel.
19 | AI | Evals & guardrails | docs/03-architecture.md ADR-4 | Create 10 seeded failures with known root causes and score the agent. | How do you measure an AI feature before production? PII in prompts? | Done. Corners: 16 seeded scenarios incl. UNKNOWN/NO_ISSUE negatives, 100% score; abstain instead of guess; LLM prompt excludes row data; LLM failure falls back to rules; symptom length cap 500 (422); UI warns when UNKNOWN. Not covered: real-LLM drift, adversarial symptom text.
20 | Frontend | React + TypeScript + dev proxy | console/src/App.tsx, vite.config.ts | Add an exceptions table that calls /orchestrator/api/runs/{id}/exceptions. | How does the dev proxy avoid CORS? Controlled vs uncontrolled state? Error/loading states? | Mostly done: runs/recon/exceptions/mapping review/Diagnose panel, 19 tests. Corners: errors shown with role=alert; buttons disabled while busy; api failures typed via ApiError; import type + no enums (erasableSyntaxOnly); two proxies /orchestrator and /ai; mocked-api tests with vi.mock. Polling: 5s setInterval with cleanup, stops on terminal states, tested with fake timers. Gap: no e2e/browser test. UX: stepper mirrors the server state machine (runState.ts); badge colour by outcome; keyboard focus styles. E2E: Playwright (webServer array boots 3 services, channel msedge) covers create/advance/diagnose in a real browser. Gap: no CI job for e2e yet.
21 | Quality | Testing strategy (unit, integration, fixtures) | src/test/... , ai-service/tests | Add a test that fails if a new cleansing rule is added without a quarantine reason. | Test pyramid? What did your tests catch? (Answer: the NUMBER(14,2) YAML bug.) | Done: pyramid of 75 checks + 16 evals (docs/05). Corners: unique H2 db per test class, MockMvc vs real HTTP, fake HTTP server for LLM and AI-client tests, Playwright e2e. Gaps: no contract/load/concurrency tests, nothing on real Oracle.
22 | Quality | CI pipelines | .github/workflows/ci.yml | Push to GitHub, break a test on purpose, read the failing run. | What belongs in CI? How do you keep builds fast and reliable? | File done, never run on GitHub: 4 jobs (orchestrator, ai-service, console, e2e with Playwright Chromium). Corner: e2e config uses installed Edge locally and Chromium when CI=true.
23 | Ops | Observability (logs, metrics, traces, alerts) | actuator endpoints in application.yml | Add a custom Micrometer counter 'rows_quarantined' and graph it. | Which metrics would you alert on during a cutover? Logs vs metrics vs traces? | Partially: Micrometer counters/timer with tags, asserted in MetricsTest, visible at /actuator/metrics. Corners: count after commit; keep tag values bounded (reason codes, not ids) to avoid cardinality blowups. Not built: export, dashboards, traces, alerts.
24 | Ops | Containers & local infra | docker-compose.yml | Install Docker, run compose, connect to Oracle and Postgres with a client. | Image vs container? How do you debug a service that works locally but not in the customer environment? | Not yet built (Docker missing)
25 | Security | Multi-tenancy, secrets, PII | TENANT_ID columns, env-based credentials | Prove one tenant's query can never see another tenant's rows; mask PII in logs. | Tenant isolation strategies? How do you handle secrets and PII in a customer environment? | Partially: authentication and roles built and tested (SecurityApiTest, e2e wrong-password), secrets from env with no defaults, PII-free prompts, no RAW_PAYLOAD in API, approval gates, audit, parameterised SQL; review docs/06 (S1, S2 closed in code). Still open: OIDC/JWT for production. Cross-tenant isolation now tested (TenantIsolationTest: same legacy files for two tenants do not mix; tampering in one tenant never appears in another tenant shadow diff, reconciliation scoped per tenant). |  | STAR: Situation: approvals were a typed name, so nobody could be held accountable. Task: add real authn/z fast without a customer IdP. Action: stateless Basic auth, 4 roles, actor taken from the login (request-body names ignored), env-only secrets, READER service account for the agent, cross-tenant tests. Result: S1/S2 closed in code; found that a 401 with WWW-Authenticate hangs browser fetch (headless e2e caught it), so the API returns a bare 401 and the UI verifies at sign-in. Next: OIDC/JWT.
26 | FDE core | Cutover, rollback & runbooks | docs (runbook pending) | Write a one-page cutover runbook and rehearse a rollback. | Walk me through a zero-downtime cutover. When do you abort? | Done on H2: runbook, 3 pre-checks, approval gate, rollback drill with audit trail. Corners: rollback only from FREEZE..MONITOR; ROLLED_BACK terminal; READY needs clean shadow diff. Missing: feature flags, real switch, CDC final sync.
27 | FDE core | Customer communication & handover | docs (signoff pack pending) | Write a status update to a non-technical COO after a failed load. | How do you explain a delay or failure to a customer? What is in a handover pack? | Done (docs): COO status update, failure-update template, signoff checklist with honest open items in docs/07. Interview angle: say what is proven, what is not, what you need from the customer, and do not promise a date before the Oracle rehearsal. Final pack: docs/07 signoff checklist (13 items, CI green on GitHub, 89 automated checks) and docs/08-demo-script.md. Demo-ready, not production-ready.

## Summary
Phase | Total | Done | % Complete | Learning avg confidence
Discover
Design |  |  |  | Topics rated
Build
Test
Signoff
Overall

## Pending & Dependencies
# | Pending item | Requirement | Blocked by | Type | What is needed to finish | Current workaround / what is proven
1 | Run against real Oracle target | Goal G1/G2, FR3, FR6 | Docker not installed | Install | Docker Desktop, Oracle XE container, point TARGET_DB_URL at it, rerun the test suite and load | All logic proven on H2 in Oracle mode (66k-row run, reconciliation ties out)
2 | CDC via Kafka and Debezium, final sync | FR4, FR9, NFR lag p95 < 5 s | Docker not installed | Install | Docker Compose with PostgreSQL, Kafka, Debezium; build the consumer and final-sync step | Event contract in docs/contracts/kafka-events.md; state machine and pre-checks already gate FINAL_SYNC
3 | PostgreSQL as the legacy source | Decision 1 in docs/01 | Docker not installed | Install | PostgreSQL container and a source reader | Legacy data is read from CSV files
4 | Real LLM for mapping and diagnosis quality | Goal G4 (measured on a real model) | Corporate web filter (Zscaler) blocks model download | Access / IT | Allow registry.ollama.ai or provide a hosted OpenAI-compatible endpoint and key | Rule-based agent scores 16/16 on evals; HTTP LLM path tested against a fake server; Ollama is installed
5 | OIDC/JWT single sign-on | NFR role-based access | Needs an identity provider | Access / IT | IdP details (issuer, client), swap Basic auth for resource-server JWT | Basic auth, 4 roles, actor from login, tested
6 | Throughput proof (>= 5k rows/s) and CDC lag | NFR throughput | Needs Oracle and a production-size run | Install | Run the 400k-loan / 6M-payment load on the real target | 66k rows measured on H2 only
7 | DLQ and replay view in the console | FR9, FR11 | Depends on item 2 (no DLQ exists without Kafka) | Build after item 2 | DLQ API plus console panel | Exceptions (quarantined rows), reconciliation, profile, diagnose panels exist
8 | Agent chat and traces/alerts | FR11, NFR observability | Time; traces need a collector (install) | Build / Install | Chat UI, OpenTelemetry collector, alert rules | Metrics (Micrometer) and a single-question diagnose panel
9 | Body-schema contract tests, PII masking check in logs | NFR security, G2 | Time only | Build | Validate bodies against OpenAPI; scan logs for PII | Endpoint-level contract test; PII-free prompts and API
10 | Customer approver and negative-amount owner named; sign-off names and dates | docs/07 checklist item 10 | Needs the business | Business | Names from the customer | Open items listed in docs/07